## Sheet1
No | Parent_No | Request Date | Target Date | Requestor | Requestor_email | Category | Details | Status | Status Start Time | Quantity | Material | Color | Completed Date | Status History | Admin Comments
1 |  | 4/5/2026 | 1/6/2026 | chchoonw | choonwee.chua@infineon.com | Innovation | Project: Sodium EPAD Klusa: G-3000-37PB0242-00-0-00 | 3D drawing processing | 18/06/2026 01:35 | 1 | PLA | Grey |  | [{"Status": "Review Drawing", "Date": "04/05/26 07:30"}, {"Status": "3D drawing processing", "Date": "18/06/26 01:35", "Admin Comments": ""}]
2 |  | 13/5/2026 | 20/5/2026 | uyao | christianjayandal.uyao@infineon.com | others | Inspection Jig with 45 degree angle positioning | Completed | 10/06/2026 02:54 | 2 | PLA | Black | 10/06/2026 02:54:16 | [{"Status": "Review Drawing", "Date": "13/05/26 07:48"}, {"Status": "Completed", "Date": "10/06/26 02:54", "Admin Comments": ""}]
3 |  | 13/5/2026 | 20/5/2026 | widhiasih | gati.widhiasih@infineon.com | YIP/Improvement | please follow the attachment file for reference | Review Drawing | 13/5/2026 9:28:00 am | 2 | PETG | White |  | [{"Status": "Review Drawing", "Date": "13/05/26 09:28"}]
4 |  | 25/5/2026 | 25/5/2026 | bahadi | bahadi.bahadi@infineon.com | YIP/Improvement | Pusher & stoper magazin Twingan CD&PL process | Review Drawing | 25/5/2026 04:18 | 1 | PLA | Black |  | [{"Status": "Review Drawing", "Date": "25/05/26 04:18"}]
5 |  | 09/06/2026 | 16/06/2026 | mathewjo | joemathew.john@infineon.com | Innovation | test-deployment | Rejected | 15/06/2026 03:44 | 1 | PLA | Black | 09/06/2026 07:07:24 | [{"Status": "Review Drawing", "Date": "09/06/26 06:28"}, {"Status": "Rejected", "Date": "09/06/26 06:29", "Admin Comments": ""}, {"Status": "Completed", "Date": "09/06/26 07:07", "Admin Comments": ""}, {"Status": "Buy-off", "Date": "15/06/26 03:44", "Admin Comments": ""}, {"Status": "Rejected", "Date": "15/06/26 03:44", "Admin Comments": ""}]
6 |  | 09/06/2026 | 26/06/2026 | lauyewannand | yewannandrew.lau@infineon.com | YIP/Improvement | improvement for oxidation | Printing Process | 17/06/2026 01:38 | 1 | PAHT-CF | Black |  | [{"Status": "Review Drawing", "Date": "09/06/26 07:24"}, {"Status": "3D drawing processing", "Date": "15/06/26 08:53", "Admin Comments": ""}, {"Status": "Printing Process", "Date": "17/06/26 01:38", "Admin Comments": ""}]
7 |  | 10/06/2026 | 17/06/2026 | saefudin | faik.saefudin@infineon.com | Others | Urgent request for release A7.1 and A9 TF2 Tooling LDSO-6-2 150MILS to plug empty space after remove forming punch from 4UP to 2UP | Completed | 17/06/2026 01:12 | 4 | PLA | Black | 17/06/2026 01:12:23 | [{"Status": "Review Drawing", "Date": "10/06/26 01:51"}, {"Status": "3D drawing processing", "Date": "15/06/26 04:03", "Admin Comments": ""}, {"Status": "Printing Process", "Date": "17/06/26 01:10", "Admin Comments": ""}, {"Status": "Buy-off", "Date": "17/06/26 01:11", "Admin Comments": ""}, {"Status": "Completed", "Date": "17/06/26 01:12", "Admin Comments": ""}]
8 |  | 10/06/2026 | 15/06/2026 | casicas | bryanlimpio.casicas@infineon.com | Others | TDSON LSS (100x300m leadframe) inspection jig for package crack. | Completed | 17/06/2026 01:11 | 1 | PETG | White | 17/06/2026 01:11:39 | [{"Status": "Review Drawing", "Date": "10/06/26 04:19"}, {"Status": "Buy-off", "Date": "15/06/26 04:05", "Admin Comments": ""}, {"Status": "Completed", "Date": "17/06/26 01:11", "Admin Comments": ""}]
9 |  | 15/06/2026 | 22/06/2026 | fadilaannisa | annisadhiya.fadila@infineon.com | Innovation | Please help to create conversion kit for Fast Prototype Twin Gan material. | Printing Process | 18/06/2026 01:33 | 1 | PETG | Black |  | [{"Status": "Review Drawing", "Date": "15/06/26 03:52"}, {"Status": "3D drawing processing", "Date": "15/06/26 08:53", "Admin Comments": ""}, {"Status": "Printing Process", "Date": "18/06/26 01:33", "Admin Comments": ""}]
10 |  | 03/07/2026 | 10/07/2026 | hasibuaninda | indahholijah.hasibuan@infineon.com | Innovation | We need to create partition for spare part storage WB. for temporary detail, the plan partition is have 2 row and 4 column currently, we don't have drawing available. | 3D drawing processing | 06/07/2026 03:04 | 1 | PLA | Black |  | [{"Status": "Review Drawing", "Date": "03/07/26 07:35"}, {"Status": "3D drawing processing", "Date": "06/07/26 03:04", "Admin Comments": ""}]
11 |  | 08/07/2026 | 31/07/2026 | bilashifasal | shifasalsa.bila@infineon.com | Innovation | This Jig will be used for DA and DMC Data Gathering in CT300. | Review Drawing | 08/07/2026 08:51 | 1 | PLA | White |  | [{"Status": "Review Drawing", "Date": "08/07/26 08:51"}]